EU Project:	Professionalization of Literacy and Basic Education –

Basic Modules for Teacher Training: TRAIN

Reference-No:     229564-CP-1-2006-1-DE-GRUNDTVIG-G1

Monitoring Report 3

Reporting partner: SVEB

Reporting period:	01. October 2007 – 31. December 2007

Introduction:

As described in the project proposal it is planned to write regularly monitoring reports.

The reports should include information on:

- information about the progress

- communication within the project

- involvement of experts and establishment of network

- dissemination activities

- development of concept/module

- difficulties and weak points

- recommendations.

Remark: The frames are adaptable to the length of your answers.

Aspects for Monitoring Report

Progress of project

- activities undertaken during the reporting period

- Preperation of partner meeting in Ireland

- Active participation in partner meeting in Irealand (3 days)

- Mandating an Austrian Expert (Antje Doberer-Bey, VHS Floridsdorf) to compile a country report for the situation in Austria.

- Finalize the country reports Switzerland and Liechtenstein

- Continuous communication with the project coordinator

- successful experiences and / or events

- The partner meeting in Ireland was well organised and productive. We had good results.

- Fruitful cooperation with the Austrian expert for the country report.

- difficulties and weak points

- We still have not received the minutes from the Ireland meeting.

- We sill wait for the results for the profile of competences from the Slovenian and the Irish partner.

- feedback from others regarding the project

- positive feedback from the Austrian partner

Involvement of experts and establishment of local network within TRAIN

- With whom did you work together?

- With the Austrian expert

- What have you done so far? What are your experiences?

- fruitful cooperation for the country report.

Dissemination

- What are your dissemination tools? (e.g. networks, magazines, newsletters…)

- Website www.alice.ch / Newsletter SVEB

- Workshops  / Documentation

- Local network on literacy

- General Assembly

- Working papers, i.e. the country reports

- What have you done? - Overview of activities in general (in addition: please fill in the specific “dissemination form”)

- Please see separate dissemination report.

Development of modules

- Further steps

We do not develop a module.

- Country specific aspects or interests

- Open questions

Remarks, questions and / or recommendations

- Regarding the reporting period

- Regarding the further steps

We look forward to the piloting of the DIE module in Switzerland next year.

- Regarding the cooperation between the partnership

City / Date: Zurich, 19. December

Report compiled by: Bernhard Grämiger, SVEB