EU Project:	Professionalization of Literacy and Basic Education –

Basic Modules for Teacher Training: TRAIN

Reference-No:     229564-CO-1-2006-1-DE-GRUNDTVIG-G1PP

Monitoring Report 1

Reporting partner: National Agency to Fight Illiteracy (ANLCI)

Reporting period:	1 October 2006 – 15 June 2007

Introduction:

As described in the project proposal it is planned to write regularly monitoring reports.

The reports should include information on:

- information about the progress

- establishment of local network

- development of concept with interviews with learners

- difficulties and weak points

- strategies of problem solving.

Remark: The frames are adaptable to the length of your answers.

Aspects for Monitoring Report

Progress of project

- activities undertaken during the reporting period

- Presentation of the project

- Preparation document for the kick-off meeting

- Overview of the financial aspects and reporting documents

- Collect of the materials, preparation and finalisation of the national report

- Information meeting on 6th February gathering experts on teachers’ training

- successful experiences and / or events

- Information meeting gathering experts

- Interviews of consultants and project coordinators

- difficulties and weak points

- Delays and time consuming preparation of the Permanent forum of the best practices (the permanent forum, emphasizing the enhancement of stakeholders’ professionnalization, has strong links with TRAIN).

- The small size of the ANLCI team and its overload of work.

- Delays in the preparation of the national data of training establishments/institutions offering basic skills teachers’ training.

- Difficulties concerning the necessity of writing in English.

- feedback from others regarding the project

- Interest shown on the sharing of practices

- Interest on having a list of basic skills teachers’ training establishments

- Interest on other European countries teachers’ training modalities

- Expectations regarding the TRAIN modules

Involvement of experts and establishment of local network within TRAIN

- With whom did you work together?

Project coordinators and experts in charge with teachers’ training courses and Literacy resource centres (information meeting 6th February);

Consultants of the Scientific Committee

- What have you done so far? What are your experiences?

- Presentation

- Dissemination

- Drafting of the national report

Dissemination

- What are your dissemination tools? (e.g. networks, magazines, newsletters…)

- Posters

- Flyers

- What have you done? - Overview of activities in general (in addition: please fill in the specific “dissemination form”)

- Salon de l’Education (Paris) : National show on Education

- National workshop gathering experts on professionalization of trainers (6th Feb 2007)

- ANLCI Board meeting

- Preparation of material for dissemination on the national meeting of the Permanent Forum of the best practices (20 – 22 June 2007)

Development of modules

- First steps

Not there yet

- Country specific aspects or interests

It has not been raised yet

- Open questions

Remarks, questions and / or recommendations

- Regarding the reporting period

Difficulties concerning translating aspects

- Regarding the further steps

- Regarding the cooperation between the partnership

The coordinator has been kindly understanding.

City / Date: Lyon, 28th June 2007

Report compiled by: Elie MAROUN