EU Project:	Professionalisation of Literacy and Basic Education –

Basic Modules for Teacher Training: TRAIN

Reference-No:     229564-CP-1-2006-1-DE-GRUNDTVIG-G1

Monitoring Report 2

Reporting partner:	SVEB

Reporting period:	16 June 2007 – 9 October 2007

Introduction:

As described in the project proposal it is planned to write regularly monitoring reports.

The reports should include information on:

- information about the progress

- establishment of local network

- development of concept for interviews with learners

- difficulties and weak points

- strategies of problem solving.

Remark: The frames are adaptable to the length of your answers.

Aspects for Monitoring Report

Progress of project

- activities undertaken during the reporting period

- Finalizing the questionnaire “Profile of Competences of Literacy Teachers”

- Writing of a short news text on the meeting in Switzerland attn. the DIE

- Dispatch of the Profile of Competences to Swiss Experts in the literacy field

- Exchange on the Questionnaire with the Experts by e-Mail.

- Evaluation of the experts’ responses and writing of reports both in German and English

- Update of the Swiss project website on www.alice.ch

- Numerous contacts with Swiss experts on the topic of professionalisation of literacy teacher training and exchange on the TRAIN project.

- Update of the country reports Switzerland and Liechtenstein

- Continuous communication with the project coordinaton

- successful experiences and / or events

- The involvement of Swiss experts in the questionnaire was very much appreciated.

- The evaluation of the experts’ responses gives an interesting starting point for further discussion both on the international and national level.

- difficulties and weak points

- The methodology of the questionnaire has it flaws, e.g. it’s bias towards the nomination “very important”. To be discussed in the next partner meeting.

- feedback from others regarding the project

- Many positive feedbacks to the usefulness of the TRAIN project in general.

- Some hints on the methodical flaws of the questionnaires.

Involvement of experts and establishment of local network within TRAIN

- With whom did you work together?

- With Swiss experts and literacy teachers across Switzerland.

- What have you done so far? What are your experiences?

- see above.

Dissemination

- What are your dissemination tools? (e.g. networks, magazines, newsletters…)

- Website www.alice.ch / Newsletter SVEB

- Workshops  / Documentation

- Local network on literacy

- General Assembly

- Working papers, i.e. the country reports

- What have you done? - Overview of activities in general (in addition: please fill in the specific “dissemination form”)

- Please see separate dissemination report.

Development of modules

- First steps

Our organisation will not develop a module, but test one of them.

- Country specific aspects or interests

-

- Open questions

-  What module to test in Switzerland?

-  What about the language problem?

-  When will the modules be ready to be tested?

Remarks, questions and / or recommendations

- Regarding the reporting period

-

- Regarding the further steps

-  the

-

- Regarding the cooperation between the partnership

- Communication tends to be more intensive before and after partner meetings.

City / Date 	Zurich / October 9, 2007

Report compiled by: Bernhard Grämiger, SVEB