EU Project:	Professionalization of Literacy and Basic Education –

Basic Modules for Teacher Training: TRAIN

Reference-No:     229564-CP-1-2006-1-DE-GRUNDTVIG-G1

Monitoring Report 3

Reporting partner: German Institute for Adult Education (DIE)

Reporting period:	01. October – 31. December 2007

Introduction:

As described in the project proposal it is planned to write regularly monitoring reports.

The reports should include information on:

- information about the progress

- communication within the project

- preparation of progress report

- involvement of experts and establishment of network

- dissemination activities

- development of concept (as preparation for the module)

- difficulties and weak points

- strategies of problem solving.

Remark: The frames are adaptable to the length of your answers.

Aspects for Monitoring Report

Progress of project

- activities undertaken during the reporting period

Project management

Dissemination activities (s. overview of dissemination)

Monitoring and evaluation

Further development of module 5: Learning Counselling

Preparation of 3rd partner meeting in Ireland

Development of a framework for the qualification concept

Announcement of seminar (piloting module 5: Learning Counselling)

- successful experiences and / or events

- Positive feedback from national and European colleagues; they are interested in getting involved in the project

- difficulties and weak points

- feedback from others regarding the project

Experts and practitioners are very interested in the project.

Involvement of experts and establishment of local network within TRAIN

- With whom did you work together?

German and European researchers and ABE professionals

- What have you done so far? What are your experiences?

See above

Dissemination

- What are your dissemination tools? (e.g. networks, magazines, newsletters…)

DIE Magazine

DIE Newsletter

TRAIN Newsletter

DIE and TRAIN website

DIE nationwide network regarding literacy and basic education

Network across Europe

Conferences and meetings

- What have you done? - Overview of activities in general (in addition: please fill in the specific “dissemination form”)

Conferences and workshops

TRAIN Newsletter

(s. overview on dissemination)

Development of modules

- Further steps

Draft of module

Gathering materials for the module

Further discussions with project managers concerning the module – content, date, duration

- Country specific aspects or interests

For DIE as coordinator it is important to analyse European developments and trends in order to strengthen the field of literacy and basic education in Germany – especially concerning professionalization.

Learning counselling has a tradition and currently there are some interesting new developments.

- Open questions

Remarks, questions and / or recommendations

- Regarding the reporting period

Framework and further tasks are clear.

- Regarding the further steps

We will meet the commitments.

- Regarding the cooperation between the partnership

See above

City / Date Bonn, 12th of January  2008

Report compiled by: Monika Tröster