EU Project:	Professionalization of Literacy and Basic Education –

Basic Modules for Teacher Training: TRAIN

Reference-No:     229564-CP-1-2006-1-DE-GRUNDTVIG-G1

Monitoring Report 3

Reporting partner: National Agency to Fight illiteracy (ANLCI)

Reporting period:	01. October 2007 – 31. December 2007

Introduction:

As described in the project proposal it is planned to write regularly monitoring reports.

The reports should include information on:

- information about the progress

- communication within the project

- involvement of experts and establishment of network

- dissemination activities

- development of concept/module

- difficulties and weak points

- recommendations.

Remark: The frames are adaptable to the length of your answers.

Aspects for Monitoring Report

Progress of project

- activities undertaken during the reporting period

- Presentation of the project and dissemination activities during ANLCI meetings (national meeting with the ANLCI regional project leaders; national meeting of the members of the Advisory Committee of the ANLCI; presentation during the Education Partner Show;

- Publication of an article in the ANLCI newsletter Anlci Infos

- Organisation of two ICT expert committee meetings concerning the elaboration of the TRAIN module 4

- Development and updating of module 4 documents

- Participation to the TRAIN Waterford meeting (Ireland) 14th  to 17th October

- Elaboration and launching of call for application to take part to the experimentation of the TRAIN module 4, planed in February 2008

- Selection of trainers’ trainers to test the module and preparation meetings.

- Selection of trainees who are going to test the module

- Preparation of the provisional programme for the national meeting (14th May) presenting the results of module 4 experimentation.

- successful experiences and / or events

- Call for application (49 answers was received from all regions)

- Elaboration of the sequences of the module

- difficulties and weak points

- Choice of a content corresponding to a common interest suitable to the various categories of trainers concerned by the Literacy and Basic education

- Necessity for us - as a national agency - to consult official partners and training operators to open the selection to all trainer categories.

- feedback from others regarding the project

-	People informed (i.e. during meetings) are interested by the announced modules and the test on the TIC one

-	Some are careful regarding implementation without continuing actions supported by local organisations

-	Interest for an operational European project, providing support to trainers

-	High motivation of the experts regarding the experimentation of TRAIN module 4 and for its architecture (modalities)

Involvement of experts and establishment of network within TRAIN

- With whom did you work together?

- With the ANLCI team, university teachers and experts in charge with teachers’ training

- With 9 experts using ICT and individual learning system

- What have you done so far? What are your experiences?

- Information concerning the actions and the elaborated documents

- Consultation prior to the preparation of the test and of the national meeting

- Consultation the selection of the applicants

Dissemination

- What are your dissemination tools? (e.g. networks, magazines, newsletters…)

- Dissemination through the ANLCI network during meetings and using the ANLCI communication tools (website, newsletter …)

- The TRAIN flyers and an other document concerning European projects were sent to the ANLCI regional project leaders and to the resource centres

- The ANLCI website (publication of the call to applications, presentation of the module and the TRAIN project

- Interview to be published in the Burgundy Resource centre’s newsletter

- What have you done? - Overview of activities in general (in addition: please fill in the specific “dissemination form”)

- Exchanges with the experts (expansion of the potential networks)

- Diffusion of the flyer,

- Diffusion of presentation documents on the project and the module

Development of modules

- Further steps

- Realisation of the various steps of the experimentation of the module.

- Preparation of the national meeting which will present the experimentation results

- Presentation of the TRAIN tools (national reports, questionnaire results and module 4 experimentation results) in the next national meeting of the training trainers institutions

- Country specific aspects or interests

The large interest showed for the TRAIN module, referring to the wide number of applications; show that training operators are eager to develop ITC uses.

Trainers are looking to be trained on the various uses of tools available on the French market, and to develop new training systems – especially in distance training.

- Open questions

Can we produce for the countries represented in the TRAIN team a common list of the Learning tools supported by the ICT?

Remarks, questions and / or recommendations

- Regarding the reporting period

- Regarding the further steps

Need to stabilise the schedule of the Lyon meeting in next April

- Regarding the cooperation between the partnership

City / Date: Lyon, January 21, 2008

Report compiled by: Elie MAROUN, ANLCI