- EU Project:	visuaLearning

Reference-No:     225773-CP-1-2005-1-DE-GRUNDTVIG-G1

- Monitoring Report 4

- Reporting partner: DIE/Germany

- Reporting period:	1. December 2006 – 30. April 2007

- Introduction:

- As described in the project proposal it is planned to write regularly monitoring reports.

The reports should include information on:

- information about the progress

- establishment of local network

- development of group discussions with learners

- preparation of qualification workshops

- development of qualification concept

- difficulties and weak points

- strategies of problem solving.

- Remark: The frames are adaptable to the length of your answers.

- Aspects for Monitoring Report

- Progress of project

- activities undertaken during the reporting period

- Involvement of new project partner from The Netherlands

- Development of outline for group discussions with learners

- Carrying out of 1st group discussion

- Analysis of 1st group discussion

3rd Partner Meeting in Bonn/Germany

- Preparation of Qualification Workshop in Bonn/Germany

- Carrying out qualification workshop

- Revision of concept

- successful experiences and / or events

The partnership was very engaged and had intensive discussion during the meeting and after the workshop in Bonn.

- difficulties and weak points

Further changes in the project: new partner and new colleagues who have to be informed and integrated

- feedback from others regarding the project

- Positive feedback, interested in cooperation

- Group discussions with learners

- Description of target group(s)

The target group were literacy students and migrants on a more or less literacy level.

- Results and findings

- The discussions had been taped and later transcribed.

The findings are very interesting. They describe very detailed in the reports according to the guidelines we developed and agreed upon.

- Consequences for the workshops and the qualification concept

The group discussion will be a good “introduction” and support to carry out the workshops.

We will present the main findings of the group discussion in the starting phase of the workshop. The participants probably will appreciated it very much and it will be easier for them to take part, there will be a common understanding concerning the target group and they will feel invited to contribute their experiences.

- Involvement of experts and establishment of local network

- With whom did you work together?

- We are still working in the network in three different cities:

- Community College in Bonn

- Community College in Eschweiler

- Berami in Frankfurt

Furthermore we work together with nationwide associations in the field of literacy and basic education to promote visual learning.

- What have you done so far? What are your experiences?

- The cooperation and promotion is very successful.

- Dissemination

- What are your dissemination tools? (e.g. networks, magazines, newsletters…)

- DIE Magazine

- DIE Newsletter

visuaLearning newsletter

- DIE and visuaLearning website

- DIE nationwide network regarding literacy and basic education

- Network across Europe

- Conferences, meetings and study visits on a national and European level

- What have you done? - Overview of activities in general (in addition: please fill in the specific “dissemination form”)

- Newsletters

- Presentations during conferences, meetings etc.

- See dissemination form for further details

- Development of qualification concept

- First steps

We informed partner within our network about the workshops. Some very  enthusiastic and some hesitated. We had to strengthen our public relation work but then it worked very good. The date for the first workshop is already fixed. It will take place in Frankfurt.

- Country specific aspects or interests

- Emphasize the importance of visual learning

- Strengthen the methodological knowlegde

- Strengthen the awareness concerning visual competences

- Open questions

- We have to find a common framework for the presentation of concept.

- Preparation and testing of qualification workshop

- First steps

- Promotion of workshops

- Involving partners from local networks

- Country specific aspects or interests

- Emphasize the importance of visual learning

- Strengthen the methodological knowlegde

- Strengthen the awareness concerning visual competences

- Open questions

- We have to find a common framework for the presentation of concept

- Further steps

- Revision of concept

- Remarks, questions and / or recommendations

- Regarding the reporting period

The tasks all partners had to fulfil were challenging but all in all very interesting and successful.

The communication should be more focused on content and progress then on reminders.

- Regarding the further steps

- Intensify the communication among the partnership

- Regarding the cooperation between the partnership

As the coordinator I would appreciate if all partners would keep their commitments.

- City / Date: Bonn, 4th of May 2007

- Report compiled by: Monika Tröster